## Summary 2024
Risk reference. | Risk title | Risk tolerance range | Previous quarter total risk score | Current total risk score | Control effectiveness | Risk score versus risk tolerance
A | IORP II compliance | Zero risk tolerance range: 0-4 | 10 | 10 | 50% | Above range
B | Key person risks | Low risk tolerance range: 5-10 | 8 | 10.4 | 35% | Above range
C | Failure to deliver a strategic project | Zero risk tolerance range: 0-4 | 8 | 8 | 60% | Above range
D | Adequacy of the Authority's income | Zero risk tolerance range: 0-4 | 4 | 4 | 50% | Within range
E | Management capacity | Zero risk tolerance range: 0-4 | 4 | 4 | 75% | Within range
F | Auto enrolment (AE) | Low risk tolerance range: 5-10 | 1.5 | 1.5 | 25% | Within range
G | Negative impact of hybrid work model (HWM) | Low risk tolerance range: 5-10 | 2.4 | 2.4 | 60% | Within range
H | Lack of specific technical pensions expertise | Low risk tolerance range: 5-10 | 1.8 | 1.8 | 80% | Within range
I | Poor quality or insufficient data | Zero risk tolerance range: 0-4 | 1.6 | 1.6 | 80% | Within range
J | IT hardware and systems access | Zero risk tolerance range: 0-4 | 1.6 | 1.6 | 80% | Within range
K | Cybersecurity | Zero risk tolerance range: 0-4 | 1.6 | 1.6 | 80% | Within range
L | Data breach | Zero risk tolerance range: 0-4 | 1.2 | 1.2 | 80% | Within range
M | Corporate Governance non-compliance | Zero risk tolerance range: 0-4 | 0.8 | 0.8 | 90% | Within range

## 2024 Risks
Risk reference. | Risk title | Risk description | Possible causes of the risk coming to pass | Consequences for delivery of the Authority strategy | Risk category | Who is responsible | Controls | Risk score by quarter | Impact (1-5) | Likelihood (1-5) | Sub total risk score = Impact x Likelihood | Control effectiveness as a % (where 100% is very effective and very good controls are in place) | Total risk score (Sub total risk score is reduced by the control effectiveness %) | Previous quarter total risk score | Current total risk score | Risk tolerance range | Risk score versus risk tolerance | Control effectiveness % is increasing or decreasing | Date and detail of any comments or changes to risks by PR, SMT, ARC or Authority members. | Proposed new controls | Action required to implement new control | Timeline for new control to be implemented
A | IORP II compliance | Poor or low standards of compliance with IORP II obligations by regulated entities. | Difficulty in applying effective forward-looking risk-based supervision (FLRBS) because of: - the lack of a specific powers under the Pensions Act to enforce some of our expectations - difficulty in finding legislative space to progress master trust authorisation and general authorisation despite ongoing engagement from DSP - the significant number of schemes still remaining. Legal challenge in relation to compliance responses. A significant non-compliance case(s) takes resources away from other supervision activity. Resourcing bottlenecks in the pensions sector. | Widespread non-compliance with new requirements, either under IORP II or other EU legislation would result in the Authority having to review its strategy. The Authority is unable to supervise occupational schemes adequately, especially relating to forward-looking risk-based supervision. | Operational | GG/BK/Authority members | Continued interaction with DSP, Finance, and the Minister by the Pensions Regulator and through Authority board members to seek the legislative changes we need. The Authority is seeking urgent primary legislation to address any shortcomings. Ongoing use of our current powers. We will engage external resources to assist in dealing with a significant non-compliance case where applicable and possible. | Start Q1 | 5 | 4 | 20 | 50% | 10 | 10 | 10 | Zero risk tolerance range: 0-4 | Above range | No Change | 9/07/2024 The SMT outlook for this risk is beginning to trend downwards based on good steady progress on consolidation and encouraging compliance results from supervision engagements. However, no change to the risk scoring is proposed at this time.
[8 empty] | End Q1 | 5 | 4 | 20 | 50% | 10
[8 empty] | End Q2 | 5 | 4 | 20 | 50% | 10
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0 | 0%
B | Key person risks | Loss of a key employee(s) | Skills, knowledge and/or experience is too concentrated in one employee, and the procedures for undertaking such tasks or systems knowledge is not adequately shared with other employees or appropriately documented. Challenges in recruiting and retaining employees particularly in IT, Data and Legal with hard to replace skills and knowledge and employees in general with strong pensions knowledge Loss of employees on foot of an unpopular HWM policy. | Delays to the delivery of strategic projects. Important or critical issues are missed or not attended to. Loss of institutional knowledge. | Operational | SMs/DM | Ensure that all key risk tasks are identified and documented, and additional employees are trained to carry out these tasks where possible. We have a key person risk register in place that is reviewed regularly. We will contract in external support to fill a skill gap in an emergency where possible. We will conduct periodic audits of qualifications and skills needed. | Start Q1 | 4 | 4 | 16 | 50% | 8 | 8 | 10.4 | Low risk tolerance range: 5-10 | Above range | Decreasing | 09/07/2024 The SMT have ongoing concerns regarding the recruitment and retention of IT and Data resources. The control effectiveness score for this risk was reduced from 50% to 35%.
[8 empty] | End Q1 | 4 | 4 | 16 | 50% | 8
[8 empty] | End Q2 | 4 | 4 | 16 | 35% | 10.4
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0
C | Failure to deliver a strategic project | Failure to deliver a strategic project on time or within budget because of project and or change management processes or implementation shortcomings. | Poor project delivery. Project sponsors or managers do not have sufficient bandwidth to exercise strong and visible sponsorship of projects and to have their finger on the pulse of risks and issues. Loss of a key person(s). Failure to recruit and retain the necessary employees to manage and deliver projects (particularly software development projects). Failure to source the necessary external resources to support the delivery of software development projects. Resistance to change organisationally limits progress in software development projects. Failure to address the significance of the technical and cultural changes required by FLRBS and IPS and the impact of these changes for technical, policy, legal, data and IT on how they do their work. Lack of inclusion of employees at sub-project management levels for the technical, regulatory, compliance and HR changes that are underway in the Authority. Change management being treated as a tick box exercise instead of as core discipline for strategy execution and benefits realisation. Other events take priority. | Failure to deliver strategic plans or their delivery is significantly delayed, particularly in the case of FLRBS and IPS. Failure to reap the expected "change" benefits from the project. Negative impact on existing and new employees and external regulated entities in adapting to the new direction of travel in how we do our work. Additional time and resources have to be spent to bring employees and external stakeholders onboard and adapt to the new operating environments particularly in relation to FLRBS and IPS. | Operational | Project sponsors/BK | We apply robust oversight of project and change management processes. Well, thought out project plan with considerable detailed specification gathering process and detailed cost estimates are in place. We will focus on both the work and the people culture side of change management. We review project expenditure as part of the quarterly management accounts process. We will engage external resources where applicable and possible. | Start Q1 | 4 | 5 | 20 | 60% | 8 | 8 | 8 | Zero risk tolerance range: 0-4 | Above range | No Change | 09/07/2024 The SMT outlook for this risk is increasing particularly in the context of the IPS project. However, no change to the risk scoring is proposed at this time.
[8 empty] | End Q1 | 4 | 5 | 20 | 60% | 8
[8 empty] | End Q2 | 4 | 5 | 20 | 60% | 8
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0 | 0%
D | Adequacy of the Authority's income | The Authority does not have enough income (cash) to do its work. | Fee income instability - due to rapid consolidation and movements from schemes to master trusts and or PRSAs Proposed changes to fee rates and structure could result in a temporary shortage in Authority income The Minister refuses or significantly delays approval for requested changes to the fee rates or fee structure. | Reduced income could result in the Authority: - not having the necessary income to deliver our objectives and requiring our objectives to be modified - having to proportionately reduce and or stop our BAU and projects work in line with the available cash. | Financial | DM/BK/Authority members | The Executive will engage directly with DSP and the Minister on any proposed changes to fee rates and fee structure as early as possible. | Start Q1 | 4 | 2 | 8 | 50% | 4 | 4 | 4 | Zero risk tolerance range: 0-4 | Within range | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 50% | 4
[8 empty] | End Q2 | 4 | 2 | 8 | 50% | 4
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0 | 0%
E | Management capacity | Management fail to deliver objectives or fail to attend to or miss important or critical issues. | The current high volume of internal and external change happening in the pensions sector. Managers undertaking new pieces of work without sufficiently taking into account the tasks involved and the resource capacity available to do the work. Failure to address new employee integration, motivation and morale issues that arise. Not being conscious enough of the potential negative impacts on employees from hybrid working and potential ongoing pandemic issues. | Failure to deliver strategic plans or their delivery is significantly delayed. Important or critical issues are missed or not attended to. Supervisory challenges and complexity arising from consolidation eg OMA, MTs, lack of clarity on PRSA rules, wind up challenges for SSAPs, schemes with complicated assets negatively impact on S&E capacity to deliver FLRBS. Reduced productivity, low levels of motivation and employee morale. Employees leave. | Operational | SMs/BK | Regular progress oversight, co-ordinated use of project management and change management methodologies across the organisation is in place. We will immediately start recruiting the additional 15 supervision employees approved in the sanction recieved in December 2023. Senior managers to involve APs more and delegate more work to them and HEOs. Eliminate non-essential work where possible. Outsource work where practical and worthwhile to help manage workload. | Start Q1 | 4 | 4 | 16 | 75% | 4 | 4 | 4 | Zero risk tolerance range: 0-4 | Within range | No Change
[8 empty] | End Q1 | 4 | 4 | 16 | 75% | 4
[8 empty] | End Q2 | 4 | 4 | 16 | 75% | 4
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0
F | Auto enrolment (AE) | Negative impact of introduction of AE | New or unplanned role for the Authority in the implementation or introduction or supervision of AE proves unmanageable due to lack of powers or resources. | Causes delays to the delivery of strategic plans for FLRBS and IPS. Additional time and resources have to be spent to bring employees and external stakeholders onboard. | Strategic | BK/AN | Continued interaction with DSP by the Pensions Regulator and the Executive on the plans for AE. We will engage external resources to assist in dealing with any additional significant AE workload where applicable and possible. | Start Q1 | 1 | 2 | 2 | 25% | 1.5 | 1.5 | 1.5 | Low risk tolerance range: 5-10 | Within range | No Change | 09/07/2024 The SMT outlook for this risk is increasing. There may be internal skills gaps and resource issues to address as AE progresses which could have some reputational impacts for the Authority but not until 2025. However, no change to the risk scoring is proposed at this time.
[8 empty] | End Q1 | 1 | 2 | 2 | 25% | 1.5
[8 empty] | End Q2 | 1 | 2 | 2 | 25% | 1.5
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0 | 0%
G | Negative impact of hybrid work model (HWM) | Potential impact of HWM on knowledge transfer and the performance of some specific work tasks. | Lack of in person engagement results in less effective employee interaction. | Negative impact on the delivery and quality of organisation objectives. Poor knowledge transfer and increased key person risk. Poor integration and training of new and existing employees. Low employee morale and motivation. | Operational | SMs/DM | HWM policy and procedures are in place Active focus on employees connecting in with each other. Guidance, information and updates are regularly communicated to all employees. Unit induction ambassadors are in place and employee assistance service is in place. Employees are provided with IT and office equipment to support hybrid working. Active employee social committee is in place. | Start Q1 | 3 | 2 | 6 | 60% | 2.4 | 2.4 | 2.4 | Low risk tolerance range: 5-10 | Within range | No Change
[8 empty] | End Q1 | 3 | 2 | 6 | 60% | 2.4
[8 empty] | End Q2 | 3 | 2 | 6 | 60% | 2.4
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0 | 0%
H | Lack of specific technical pensions expertise | Not fully understanding a specific technical pension issue that might emerge i.e. new investment or administration activity in a scheme. | Over time the administration, risk management and investment practices of schemes become very complex and we fail to understand them adequately. | The Authority is unable to assess the risks to the interest of members and beneficiaries. | Operational | GG/POS/AN | We have a panel of technical advisors in place. We have strong inter-active and information sharing arrangements in place with EIOPA, IOPS, OECD and are members of the active four way regulators group comprising Ireland, UK, Netherlands and Germany. | Start Q1 | 3 | 3 | 9 | 80% | 1.8 | 1.8 | 1.8 | Low risk tolerance range: 5-10 | Within range | No Change
[8 empty] | End Q1 | 3 | 3 | 9 | 80% | 1.8
[8 empty] | End Q2 | 3 | 3 | 9 | 80% | 1.8
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0
I | Poor quality or insufficient data | Not having quality or sufficient data to do our work efficiently and effectively. | Lack of knowledge and understanding about data in the organisation leads to poor decision-making and potentially incorrect or misleading data being used for decision-making. The design of IPS doesn't ensure data quality of a sufficiently high standard. Loss of historical data or trends with migration to the new IPS system Failure to recruit and retain the necessary employees to manage and deliver data projects. | Supervision and compliance challenges arising from having poor quality data or insufficient data across any aspect of our work. Benefits of data capture in the IPS system to support innovation in the reporting /analytics space are not maximised. Business Intelligence data warehouse not fit for new BI platform. | Operational | DOK | Well, thought out project plans with considerable detailed specification gathering processes are in place. Additional informational sessions and materials for employees regarding data, data standards, data quality and it's practical usage for risk assessment and analytics are provided. We will engage external resources where applicable and possible. | Start Q1 | 4 | 2 | 8 | 80% | 1.6 | 1.6 | 1.6 | Zero risk tolerance range: 0-4 | Within range | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q2 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0
J | IT hardware and systems access | Loss of access to IT hardware and operating systems. | Slow response times from OGCIO in dealing with issues i.e. setting up new employees or contractors with access to our network and systems. Delays from OGCIO in applying software applications or providing suitable and efficient access solutions for our third party software suppliers. Physical damage to ICT equipment (power outage, damaged cables, etc.) or a physical disaster (e.g., flooding or fire). | IT systems are unavailable and employees unable to carry out their duties. | Operational | PJK | All our IT systems except PDR are now running on OGCIO servers. Service response plan in place with OGCIO. Full back up of all databases and electronic files held off site. External ICT security audit will be carried out and the issues identified addressed. Incident Response Plan (including IT disaster recovery plan and business continuity plan) is in place. | Start Q1 | 4 | 2 | 8 | 80% | 1.6 | 1.6 | 1.6 | Zero risk tolerance range: 0-4 | Within range | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q2 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0
K | Cybersecurity | A ransomware attack or data breach due to an external hack. | A failure of ICT security measures (for example a virus getting onto our system). A ransomware attack. Data breach due to an external hack. | IT systems are unavailable and employees unable to carry out their duties. Loss of scheme data or damage to our ICT systems. The time taken to deal with the fallout from a cyber-attack or a data breach. Possible fines if the data is personal or financial loss to an individual(s) if banking data is exposed in the breach. | Operational | PJK | All our IT systems except PDR are now running on OGCIO servers. The OGCIO has a dedicated security team which monitors all these systems. External ICT security audit is carried out annually and the issues identified addressed. Incident Response Plan (including IT disaster recovery plan and business continuity plan) is in place. | Start Q1 | 4 | 2 | 8 | 80% | 1.6 | 1.6 | 1.6 | Zero risk tolerance range: 0-4 | Within range | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q2 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0
L | Data breach | Data breach due to internal employee or third-party contractor error or malice. | Lack of awareness, understanding and respect for the importance of data protection. Employee fatigue and working under pressure. Poor and careless work practices. Employees having access to data that they do not need to have access to. | Disruption to business operations. The time taken to deal with the fallout from a data breach. Possible fines if the data released is personal. Possible financial loss to an individual(s) if banking data is exposed in the breach. | Operational | DM | Data Protection and Records Management policy and procedures and Data Protection Officer in place. Ongoing data protection awareness initiatives are conducted and training for all employees and contractors is provided to ensure they understand what a data breach is. Access to HR data is restricted to HR employees and is stored in a separate folder. Safe send email alerts in place. | Start Q1 | 2 | 3 | 6 | 80% | 1.2 | 1.2 | 1.2 | Zero risk tolerance range: 0-4 | Within range | No Change
[8 empty] | End Q1 | 2 | 3 | 6 | 80% | 1.2
[8 empty] | End Q2 | 2 | 3 | 6 | 80% | 1.2
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0 | 0%
M | Corporate Governance non-compliance | Non-compliance with the Codes of Practice for State bodies and relevant statutory obligations. | Failure of internal controls. Fraud, financial maladministration or misappropriation of Authority funds or assets. | Loss of Authority money or assets. Employee's health and safety put at risk. The Authority could be prosecuted, or have to pay compensation. | Operational | DM | Good governance and internal control and finance procedures in place. We will automate internal financial procedures where possible to reduce risk of manual errors. Employee awareness activities are undertaken. SMT and ARC oversight. Internal and external audits. | Start Q1 | 4 | 2 | 8 | 90% | 0.8 | 0.8 | 0.8 | Zero risk tolerance range: 0-4 | Within range | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 90% | 0.8
[8 empty] | End Q2 | 4 | 2 | 8 | 90% | 0.8
[8 empty] | End Q3 |  |  | 0
[8 empty] | End Q4 |  |  | 0

## 2023 Risks
Risk reference. | Risk title | Risk description | Possible causes of the risk coming to pass | Consequences for delivery of the Authority strategy | Risk category | Who is responsible | Controls | Risk score by quarter | Impact (1-5) | Likelihood (1-5) | Sub total risk score = Impact x Likelihood | Control effectiveness as a % (where 100% is very effective and very good controls are in place) | Total risk score (Sub total risk score is reduced by the control effectiveness %) | Previous quarter total risk score | Current total risk score | Risk tolerance range | Risk score versus risk tolerance | Control effectiveness % is increasing or decreasing | Date and detail of any comments or changes to risks by PR, SMT, ARC or Authority members. | Proposed new controls | Action required to implement new control | Timeline for new control to be implemented
A | IORP II compliance | Poor or low standards of compliance with IORP II obligations by regulated entities. | Difficulty in applying effective forward-looking risk-based supervision (FLRBS) because of: - the large number of schemes due to low levels of consolidation - the lack of a specific powers under the Pensions Act to enforce some of our expectations - difficulty in finding legislative space to progress master trust authorisation and general authorisation despite ongoing engagement from DSP. Insufficient resources to implement FLRBS. Legal challenge in relation to compliance responses. A significant non-compliance case(s) takes resources away other supervision activity. | Widespread non-compliance with new requirements, either under IORP II or other EU legislation would result in the Authority having to review its strategy. The Authority is unable to supervise occupational schemes adequately, especially relating to forward-looking risk-based supervision. | Operational | GG/BK/Authority members | Continued interaction with DSP, Finance, and the Minister by the Pensions Regulator and through Authority board members to seek the legislative changes we need. The Authority is seeking urgent primary legislation to address any shortcomings. Ongoing use of our current powers. We will engage external resources to assist in dealing with a significant non-compliance case where applicable and possible. | Start Q1 | 5 | 4 | 20 | 50% | 10 | 10 | 10 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 5 | 4 | 20 | 50% | 10
[8 empty] | End Q2 | 5 | 4 | 20 | 50% | 10
[8 empty] | End Q3 | 5 | 4 | 20 | 50% | 10
[8 empty] | End Q4 |  |  | 0 | 0%
B | Key person risks | Loss of a key employee(s) | Skills, knowledge and/or experience is too concentrated in one employee, and the procedures for undertaking such tasks or systems knowledge is not adequately shared with other employees or appropriately documented. Challenges in recruiting and retaining employees particularly in IT, Data and Legal with hard to replace skills and knowledge and employees in general with strong pensions knowledge Loss of employees on foot of an unpopular RTO/HWM policy. Not getting approval from DSP/DPER for additional employees. | Delays to the delivery of strategic projects. Important or critical issues are missed or not attended to. Loss of institutional knowledge. | Operational | SMs/DM | Ensure that all key risk tasks are identified and documented, and additional employees are trained to carry out these tasks where possible. We have a key person risk register in place that is reviewed regularly. We will contract in external support to fill a skill gap in an emergency where possible. We will conduct periodic audits of qualifications and skills needed. Submit our employees sanction request to DSP in a timely manner. | Start Q1 | 4 | 4 | 16 | 50% | 8 | 10 | 10 | Low risk tolerance range: 5-10 | #N/A | No Change | 18/04/2023 The SMT increased the likelihood score for this risk from 4 to 5 to reflect concerns regarding the key person risk particularly as it relates to the ongoing challenges with the recruitment and retention of IT and Data personnel both as employees and contractors.
[8 empty] | End Q1 | 4 | 5 | 20 | 50% | 10
[8 empty] | End Q2 | 4 | 5 | 20 | 50% | 10
[8 empty] | End Q3 | 4 | 5 | 20 | 50% | 10
[8 empty] | End Q4 |  |  | 0
C | Failure to deliver a strategic project | Failure to deliver a strategic project on time or within budget because of project and or change management processes or implementation shortcomings. | Project sponsors or managers do not have sufficient bandwidth to exercise strong and visible sponsorship of projects and to have their finger on the pulse of risks and issues. Loss of a key person(s). Failure to recruit and retain the necessary employees to manage and deliver projects (particularly software development projects). Failure to source the necessary external resources to support the delivery of software development projects. Resistance to change organisationally limits progress in software development projects. Failure to capture the significance of the changes required by FLRBS and IPS and the impact of these changes for technical, policy, legal, data and IT on how they do their work. Lack of inclusion of employees at sub-project management levels for the technical, regulatory, compliance and HR changes that are underway in the Authority. Change management being treated as a tick box exercise instead of as core discipline for strategy execution and benefits realisation. Other events take priority. | Failure to deliver strategic plans or their delivery is significantly delayed, particularly in the case of FLRBS and IPS Failure to reap the expected "change" benefits from the project. Negative impact on existing and new employees and external regulated entities in adapting to the new direction of travel in how we do our work. Additional time and resources have to be spent to bring staff and external stakeholders onboard and adapt to the new operating environments particularly in relation to FLRBS and IPS. | Operational | Project sponsors/BK | We apply robust oversight of project and change management processes. Well, thought out project plan with considerable detailed specification gathering process and detailed cost estimates are in place. We will focus on both the work and the people side of change management. We review project expenditure as part of the quarterly management accounts process. We will engage external resources where applicable and possible. | Start Q1 | 4 | 3 | 12 | 60% | 4.8 | 4.8 | 4.8 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 4 | 3 | 12 | 60% | 4.8
[8 empty] | End Q2 | 4 | 3 | 12 | 60% | 4.8
[8 empty] | End Q3 | 4 | 3 | 12 | 60% | 4.8
[8 empty] | End Q4 |  |  | 0 | 0%
D | Adequacy of the Authority's income | The Authority does not have enough income (cash) to do its work. | Fee income instability - due to rapid consolidation and movements from schemes to master trusts and or PRSAs Proposed changes to fee rates and structure could result in a temporary shortage in Authority income The Minister refuses or significantly delays approval for requested changes to the fee rates or fee structure. | Reduced income could result in the Authority: - not having the necessary income to deliver our objectives and requiring our objectives to be modified - having to proportionately reduce and or stop our BAU and projects work in line with the available cash. | Financial | DM/BK/Authority members | The Executive will engage directly with DSP and the Minister on any proposed changes to fee rates and fee structure as early as possible. | Start Q1 | 4 | 2 | 8 | 50% | 4 | 4 | 4 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 50% | 4
[8 empty] | End Q2 | 4 | 2 | 8 | 50% | 4
[8 empty] | End Q3 | 4 | 2 | 8 | 50% | 4
[8 empty] | End Q4 |  |  | 0 | 0%
E | Management capacity | Management fail to deliver objectives or fail to attend to or miss important or critical issues. | The current high volume of internal and external change happening in the pensions sector. Managers undertaking new pieces of work without sufficiently taking into account the tasks involved and the resource capacity available to do the work. Failure to address new employee integration, motivation and morale issues that arise. Not being conscious enough of the potential negative impacts on employees from cost of living crisis, remote and hybrid working and potential ongoing pandemic issues. | Failure to deliver strategic plans or their delivery is significantly delayed. Important or critical issues are missed or not attended to. Reduced productivity, low levels of motivation and employee morale. Employees leave. | Operational | SMs/BK | Regular progress oversight, co-ordinated use of project management and change management methodologies across the organisation is in place. Senior managers to involve APs more and delegate more work to them and HEOs. Eliminate non-essential work where possible. Outsource work where practical and worthwhile to help manage workload. | Start Q1 | 4 | 4 | 16 | 75% | 4 | 4 | 4 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 4 | 4 | 16 | 75% | 4
[8 empty] | End Q2 | 4 | 4 | 16 | 75% | 4
[8 empty] | End Q3 | 4 | 4 | 16 | 75% | 4
[8 empty] | End Q4 |  |  | 0
F | Negative impact of hybrid work model (HWM) | Potential impact of HWM on knowledge transfer and the performance of some specific work tasks. | Lack of in person engagement results in less effective employee interaction. | Negative impact on the delivery and quality of organisation objectives. Poor knowledge transfer and increased key person risk. Poor integration and training of new and existing employees. Low employee morale and motivation. | Operational | SMs/DM | HWM policy and procedures are in place Active focus on employees connecting in with each other. Guidance, information and updates are regularly communicated to all employees. New employee induction plan including Unit induction ambassadors is in place and employee assistance service is in place. Employees are provided with IT and office equipment to support hybrid working. Active employee social committee is in place. | Start Q1 | 3 | 2 | 6 | 60% | 2.4 | 2.4 | 2.4 | Low risk tolerance range: 5-10 | #N/A | No Change
[8 empty] | End Q1 | 3 | 2 | 6 | 60% | 2.4
[8 empty] | End Q2 | 3 | 2 | 6 | 60% | 2.4
[8 empty] | End Q3 | 3 | 2 | 6 | 60% | 2.4
[8 empty] | End Q4 |  |  | 0 | 0%
G | Lack of specific technical pensions expertise | Not fully understanding a specific technical pension issue that might emerge i.e. new investment or administration activity in a scheme. | Over time the administration, risk management and investment practices of schemes become very complex and we fail to understand them adequately. | The Authority is unable to assess the risks to the interest of members and beneficiaries. | Operational | GG/POS/AN | We have a panel of technical advisors in place. We have strong inter-active and information sharing arrangements in place with EIOPA, IOPS, OECD and are members of the active four way regulators group comprising Ireland, UK, Netherlands and Germany. | Start Q1 | 3 | 3 | 9 | 80% | 1.8 | 1.8 | 1.8 | Low risk tolerance range: 5-10 | #N/A | No Change
[8 empty] | End Q1 | 3 | 3 | 9 | 80% | 1.8
[8 empty] | End Q2 | 3 | 3 | 9 | 80% | 1.8
[8 empty] | End Q3 | 3 | 3 | 9 | 80% | 1.8
[8 empty] | End Q4 |  |  | 0
H | Poor quality or insufficient data | Not having quality or sufficient data to do our work efficiently and effectively. | Lack of knowledge and understanding about data in the organisation leads to poor decision-making about data capture and retention. The design of IPS doesn't ensure data quality of a sufficiently high standard. Loss of historical data or trends with migration to the new IPS system Failure to recruit and retain the necessary employees to manage and deliver data projects. | Supervision and compliance challenges arising from having poor quality data or insufficient data across any aspect of our work. Benefits of data capture in the IPS system to support innovation in the reporting /analytics space are not maximised. Business Intelligence data warehouse not fit for new BI platform. | Operational | DOK | Well, thought out project plans with considerable detailed specification gathering processes are in place. Additional informational sessions and materials for employees regarding data, data standards, data quality and it's practical usage for risk assessment and analytics are provided. We will engage external resources where applicable and possible. | Start Q1 | 4 | 2 | 8 | 80% | 1.6 | 1.6 | 1.6 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q2 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q3 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q4 |  |  | 0
I | IT hardware and systems access | Loss of access to IT hardware and operating systems. | Slow response times from OGCIO in dealing with issues i.e. setting up new employees or contractors with access to our network and systems. Delays from OGCIO in applying software applications or providing access solutions for third party suppliers i.e. For our HR Time Management System, moving the door access system onto our network. Physical damage to ICT equipment (power outage, damaged cables, etc.) or a physical disaster (e.g., flooding or fire). | IT systems are unavailable and employees unable to carry out their duties. | Operational | PJK | All our IT systems except PDR are now running on OGCIO servers. Service response plan in place with OGCIO. Full back up of all databases and electronic files held off site. External ICT security audit will be carried out and the issues identified addressed. Incident Response Plan (including IT disaster recovery plan and business continuity plan) is in place. | Start Q1 | 4 | 2 | 8 | 80% | 1.6 | 1.6 | 1.6 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q2 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q3 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q4 |  |  | 0
J | Cybersecurity | A ransomware attack or data breach due to an external hack. | A failure of ICT security measures (for example a virus getting onto our system). A ransomware attack. Data breach due to an external hack. | IT systems are unavailable and employees unable to carry out their duties. Loss of scheme data or damage to our ICT systems. The time taken to deal with the fallout from a cyber-attack or a data breach. Possible fines if the data is personal or financial loss to an individual(s) if banking data is exposed in the breach. | Operational | PJK | All our IT systems except PDR are now running on OGCIO servers. The OGCIO has a dedicated security team which monitors all these systems. External ICT security audit is carried out annually and the issues identified addressed. Incident Response Plan (including IT disaster recovery plan and business continuity plan) is in place. | Start Q1 | 4 | 2 | 8 | 80% | 1.6 | 1.6 | 1.6 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q2 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q3 | 4 | 2 | 8 | 80% | 1.6
[8 empty] | End Q4 |  |  | 0
K | Data breach | Data breach due to internal employee or third-party contractor error or malice. | Lack of awareness, understanding and respect for the importance of data protection. Employee fatigue and working under pressure. Poor and careless work practices. Employees having access to data that they do not need to have access to. | Disruption to business operations. The time taken to deal with the fallout from a data breach. Possible fines if the data released is personal. Possible financial loss to an individual(s) if banking data is exposed in the breach. | Operational | DM | Data Protection and Records Management policy and procedures and Data Protection Officer in place. Ongoing data protection awareness initiatives are conducted and training for all employees and contractors is provided to ensure they understand what a data breach is. Access to HR data is restricted to HR employees and is stored in a separate folder. Safe send email alerts in place. | Start Q1 | 2 | 3 | 6 | 80% | 1.2 | 1.2 | 1.2 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 2 | 3 | 6 | 80% | 1.2
[8 empty] | End Q2 | 2 | 3 | 6 | 80% | 1.2
[8 empty] | End Q3 | 2 | 3 | 6 | 80% | 1.2
[8 empty] | End Q4 |  |  | 0 | 0%
L | Corporate Governance non-compliance | Non-compliance with the Codes of Practice for State bodies and relevant statutory obligations. | Failure of internal controls. Fraud, financial maladministration or misappropriation of Authority funds or assets. | Loss of Authority money or assets. Employee's health and safety put at risk. The Authority could be prosecuted, or have to pay compensation. | Operational | DM | Good governance and internal control and finance procedures in place. We will automate internal financial procedures where possible to reduce risk of manual errors. Employee awareness activities are undertaken. SMT and ARC oversight. Internal and external audits. | Start Q1 | 4 | 2 | 8 | 90% | 0.8 | 0.8 | 0.8 | Zero risk tolerance range: 0-4 | #N/A | No Change
[8 empty] | End Q1 | 4 | 2 | 8 | 90% | 0.8
[8 empty] | End Q2 | 4 | 2 | 8 | 90% | 0.8
[8 empty] | End Q3 | 4 | 2 | 8 | 90% | 0.8
[8 empty] | End Q4 |  |  | 0

## Risk management objectives
Risk management objectives
The objectives of the risk management framework is to assist the Authority in making informed choices which:
· identify risks which could affect the organisation’s ability to achieve its objectives and take steps to address these risks in a systematic way,
· improve business performance by providing timely risk information allowing for efficient and effective decision making and planning,
· set out the risk tolerance of the organisation so that employees can know what level of risk-taking is acceptable, and
· provide a sound basis for integrated risk management and internal control as components of good corporate governance.

## Impact parameters
Appendix I: Assessment parameters - impact
Note: Risks are rated 1 - 5 with 1 indicating low impact and 5 indicating high impact. Where risks fall into more than one category which can have different rankings e.g. a risk could be categorised as a financial risk ranked 1 (low), and an associated reputation risk ranked 5 (high) the SMT will have to make a judgement call on the overall impact of the risk.
Risk categories
Impact rating |  | Strategic impact | Financial impact (where relevant) | Operational impact | Reputational impact (samples)
Not significant | 1 | No impact on the Authority on achieving a specific strategic goal/objective. | Up to €5,000 | No impact on the effective operation of the Authority. | Low level negative findings in audit reports.
Minor | 2 | Impact is such that it does affect the Authority’s work in achieving a specific strategic goal/objective, but to an extent which is easily recoverable. | €5,000 - €50,000 | Impact is such that it does affect the effective operation of the Authority but to an extent which is easily recoverable. | Concerns being raised by Department of Social Protection (DSP).
Complaints from regulated entities or negative media comments.
Moderate | 3 | Impact is such that it curtails to some degree the Authority in achieving a specific strategic goal/objective but to an extent that is recoverable over a short period of time. | €50,000 - €100,000 | Impact is such that it significantly curtails the effective operation of the Authority but to an extent which is recoverable over a short period of time. | Public criticism from regulated entities, pensions industry, the public or the media.
Heightened concerns being raised by auditors and or DSP.
Public standing affected in the short term.
Major | 4 | Impact is such that it will make it extremely difficult for the Authority to achieve a specific strategic goal/objective. | €100,000 - €250,000 | Impact is such that it is extremely difficult for the Authority to operate effectively for an extended period of time. | Significant concerns raised by regulated entities, pensions industry, DSP and or other Government Departments.
Negative media coverage that runs over time and where public standing is affected in the longer term.
Very serious | 5 | Will prevent the Authority from achieving a strategic goal/objective. | > €250,000 | The Authority are unable to undertake ‘normal’; operations for an extended period of time. | Ministerial concern or comparable political repercussions. Complete loss of public confidence.

## Likelihood parameters
Appendix II: Likelihood of occurrence
Assessment | Description | Indicators
1 | Not likely to happen | Not likely to occur in a 5 year time period.
2 | Rarely happens | Likely to occur in a 5 year time period.
3 | Possible | Likely to occur in a 2 year time period
4 | Very likely to happen | Likely to occur in a 3-12 month time period.
5 | Almost bound to happen | Likely to occur in next 3 months

## Possible controls
Possible controls
Risk is a standing item on Unit, SMT, ARC and Authority meeting agendas.
Quarterly oversight of the risk register and management accounts by the SMT and by the ARC and reporting to the Authority.
Internal audits are conducted
Annual C&AG audit is conducted
Regular meetings with DSP.
Meetings with other Government Departments and State Agencies where relevant
Regular management oversight of policies and procedures
Risk Officer is in place
Up to date risk policy and procedures are in place
Regular (weekly, monthly, annual) checks and reconciliations are carried out particularly on fininacial activity
Employees receive regular training on operating procedures and use of data systems
Relevant insurance policies are in place
Data is backed up and stored off site.
Data is stored in password protected software systems where possible
Hard copy data is stored in locked cabinets
Personal data clean desk policy is in place
ICT external audits are consucted
Regular patching of IT systems
Data Protection Officer is in place
Regular records management reviews are conducted
Regular briefings provided to external stakehiolder pension sector representative organisations.

## Control effectiveness (hidden)
Make this a pivot table which displays the control effectiveness
The effectiveness of any controls will be estimated using a scale of 1 to 5 where 5 is “highly effective” and 1 is “no controls/controls ineffective” (increasing in 0.5 increments).
Each 0.5 increment is equal to 10% points i.e. 2 = 40% and 2.5 = 50% etc

## Risk tolerance range (hidden)
Risk tolerance range | Description
High risk tolerance range: 17-22 | The Authority is not willing to accept risks under any circumstances that may result in reputational damage, financial loss or exposure, major breakdown in information systems or information integrity, significant incidents of regulatory non-compliance, potential risk of injury to employees.
Moderate risk tolerance range: 11-16 | The Authority is willing to accept some risks in certain circumstances that may result in reputational damage, financial loss or exposure, major breakdown in information systems or information integrity, significant incidents of regulatory non-compliance.
Low risk tolerance range: 5-10 | The Authority is willing to accept some risks that may result in reputational damage or significant incidents of regulatory non-compliance.
Zero risk tolerance range: 0-4 | The Authority accepts opportunities that have an inherent high risk that may result in reputational damage.
|  |  | Risk Type | Control Effectiveness
Category | Lowest Value | Highest Value | Within range | Increasing
Zero risk tolerance range: 0-4 | 0 | 4 | Increasing within range | No Change
Low risk tolerance range: 5-10 | 5 | 10 | Above range | Decreasing
Moderate risk tolerance range: 11-16 | 11 | 16 | Unknown | Error
High risk tolerance range: 17-22 | 17 | 22